## Dashboard
Project Management Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DataReport
Project | Goal | Collected | Excluded | Remaining | Progress | Start Date | Finish Date | Due Date | Days completed | Duration (Days) | Days Remaining | Budget Given | Budget Spent
Pilot | 40 | 44 | 7 | 3 | 92.5% | 2023-09-09 | 2023-11-03 | 2023-12-08 | 40 | 65 | 25 | 3000 | 2200
Project 1 | 80 | 93 | 21 | 8 | 90% | 2024-01-08 | 2024-03-08 | 2024-03-15 | 45 | 50 | 5 | 6000 | 4650
Project 2 | 100 | 81 | 17 | 36 | 64% | 2024-02-05 | 2024-05-17 | 2024-06-07 | 75 | 90 | 15 | 6000 | 4050
Project 3 | 60 | 56 | 8 | 12 | 80% | 2024-03-11 | 2024-06-03 | 2024-06-07 | 61 | 65 | 4 | 4000 | 2800
Row Labels |  | Values | [5 empty] | Values | [5 empty] | Values
Pilot |  | Sum of Goal | 280 |  |  |  |  | Sum of Days completed | 221 |  |  |  |  | Sum of Budget Given | 19000
Project 1 |  | Sum of Collected | 274 |  |  |  |  | Sum of Duration (Days) | 270 |  |  |  |  | Sum of Budget Spent | 13700
Project 2 |  | Sum of Excluded | 53 |  | Sample collected | 78.93% |  | Sum of Days Remaining | 49 |  | Days passed | 81.85% |  |  |  | Budget spent | 72.11%
Project 3 |  | Sum of Remaining | 59 |  | Sample remaining | 21.07% |  |  |  |  | Days remaining | 18.15% |  |  |  | Budget given | 27.89%
Grand Total
Values
Sum of Collected | 274 |  | Excluded | 53
Sum of Excluded | 53 |  | Included | 221
Sum of Remaining | 59 |  | Remaining | 59
Formulas:
Days completed = NETWORKDAYS.INTL([Start Date],[Finish Date],1,N2:N26)
Duration (Days) = NETWORKDAYS.INTL([Start Date],[Due Date],1,N2:N26)
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Task
Project | Task | Assigned To | Progress
Pilot | Prepare program | AM | Completed
Pilot | Organize schedule | CH | Completed | Count of Progress | Column Labels
Pilot | Collect data | GQ | Completed | Row Labels | Completed | In progress | Upcoming | Grand Total
Pilot | Collect data | LV | Completed | Prepare program | 4 |  |  | 4
Pilot | Collect data | MW | Completed | Organize schedule | 4 |  |  | 4
Pilot | Clean data | OY | Completed | Collect data | 17 | 3 |  | 20
Pilot | Analyze data | OY | Completed | Clean data | 4 | 2 |  | 6
Pilot | Analyze data | AD | Completed | Analyze data | 3 | 2 | 1 | 6
Pilot | Share insights | AM | Completed | Share insights | 2 |  | 2 | 4
Project 1 | Prepare program | AM | Completed | Grand Total | 34 | 7 | 3 | 44
Project 1 | Organize schedule | DL | Completed
Project 1 | Collect data | GQ | Completed
Project 1 | Collect data | HR | Completed
Project 1 | Collect data | IS | Completed
Project 1 | Collect data | AD | Completed
Project 1 | Clean data | LV | Completed
Project 1 | Collect data | NX | Completed
Project 1 | Analyze data | AD | Completed
Project 1 | Share insights | AM | Completed
Project 2 | Prepare program | AM | Completed
Project 2 | Organize schedule | GQ | Completed
Project 2 | Collect data | HR | Completed
Project 2 | Collect data | IS | Completed
Project 2 | Collect data | JT | Completed
Project 2 | Collect data | KU | Completed
Project 2 | Collect data | LV | Completed
Project 2 | Collect data | OY | Completed
Project 2 | Collect data | AD | Completed
Project 2 | Clean data | PZ | Completed
Project 2 | Clean data | IS | Completed
Project 2 | Clean data | KU | In progress
Project 2 | Analyze data | AD | In progress
Project 2 | Analyze data | HR | In progress
Project 2 | Share insights | AM | Upcoming
Project 3 | Prepare program | AM | Completed
Project 3 | Organize schedule | GQ | Completed
Project 3 | Collect data | GQ | In progress
Project 3 | Collect data | HR | Completed
Project 3 | Collect data | LV | Completed
Project 3 | Collect data | MW | In progress
Project 3 | Collect data | AD | In progress
Project 3 | Clean data | PZ | In progress
Project 3 | Analyze data | OY | Upcoming
Project 3 | Share insights | AM | Upcoming

## Participant by month
Project | Month | Participant
Pilot | 2023-09-01 | 12
Pilot | 2023-10-01 | 28 | Row Labels | Sum of Participant | Month | Sample Size
Pilot | 2023-11-01 | 4 | 2023-09-01 | 12 | 2023-09-01 | 12
Project 1 | 2024-01-01 | 24 | 2023-10-01 | 28 | 2023-10-01 | 28
Project 1 | 2024-02-01 | 45 | 2023-11-01 | 4 | 2023-11-01 | 4
Project 1 | 2024-03-01 | 24 | 2024-01-01 | 24 | 2024-01-01 | 24
Project 2 | 2024-02-01 | 34 | 2024-02-01 | 79 | 2024-02-01 | 79
Project 2 | 2024-03-01 | 21 | 2024-03-01 | 60 | 2024-03-01 | 60
Project 2 | 2024-04-01 | 6 | 2024-04-01 | 13 | 2024-04-01 | 13
Project 2 | 2024-05-01 | 20 | 2024-05-01 | 42 | 2024-05-01 | 42
Project 3 | 2024-03-01 | 15 | 2024-06-01 | 12 | 2024-06-01 | 12
Project 3 | 2024-04-01 | 7
Project 3 | 2024-05-01 | 22
Project 3 | 2024-06-01 | 12

## Exclusion
Staff Initials | Project | Exclusion
CH | Pilot | 4 | Row Labels | Sum of Exclusion
GQ | Pilot | 2 | CH | 4
LV | Pilot | 1 | DL | 6
MW | Pilot | 0 | GQ | 4
OY | Pilot | 0 | HR | 2
AD | Pilot | 0 | IS | 4
DL | Project 1 | 6 | JT | 3
GQ | Project 1 | 2 | KU | 6
HR | Project 1 | 1 | LV | 4
IS | Project 1 | 2 | MW | 2
LV | Project 1 | 2 | NX | 5
NX | Project 1 | 5 | OY | 3
AD | Project 1 | 3 | AD | 7
GQ | Project 2 | 0 | PZ | 3
HR | Project 2 | 0 | Grand Total | 53
IS | Project 2 | 2
JT | Project 2 | 3
KU | Project 2 | 6
LV | Project 2 | 1
OY | Project 2 | 1
AD | Project 2 | 3
PZ | Project 2 | 1
GQ | Project 3 | 0
HR | Project 3 | 1
LV | Project 3 | 0
MW | Project 3 | 2
OY | Project 3 | 2
AD | Project 3 | 1
PZ | Project 3 | 2

## Cost
Staff Initials | Project | Month | Cost | Aggregate Cost |  |  | Month | Cost | Aggregate Cost
CH | Pilot | 2023-09-01 | 50 | 50 | Row Labels | Sum of Cost | 2023-09-01 | 150 | 150
CH | Pilot | 2023-09-01 | 50 | 100 | 2023 |  | 2023-10-01 | 150 | 300
GQ | Pilot | 2023-09-01 | 50 | 150 | Sep | 150 | 2023-11-01 | 50 | 350
CH | Pilot | 2023-10-01 | 50 | 200 | Oct | 150 | 2024-01-01 | 300 | 650
CH | Pilot | 2023-10-01 | 50 | 250 | Nov | 50 | 2024-02-01 | 950 | 1600
LV | Pilot | 2023-10-01 | 50 | 300 | 2024 |  | 2024-03-01 | 500 | 2100
GQ | Pilot | 2023-11-01 | 50 | 350 | Jan | 300 | 2024-04-01 | 400 | 2500
DL | Project 1 | 2024-01-01 | 50 | 400 | Feb | 950 | 2024-05-01 | 100 | 2600
DL | Project 1 | 2024-01-01 | 50 | 450 | Mar | 500 | 2024-06-01 | 50 | 2650
HR | Project 1 | 2024-01-01 | 50 | 500 | Apr | 400
NX | Project 1 | 2024-01-01 | 50 | 550 | May | 100
AD | Project 1 | 2024-01-01 | 50 | 600 | Jun | 50
AD | Project 1 | 2024-01-01 | 50 | 650 | Grand Total | 2650
DL | Project 1 | 2024-02-01 | 50 | 700
DL | Project 1 | 2024-02-01 | 50 | 750
GQ | Project 1 | 2024-02-01 | 50 | 800
IS | Project 1 | 2024-02-01 | 50 | 850
IS | Project 1 | 2024-02-01 | 50 | 900
LV | Project 1 | 2024-02-01 | 50 | 950
NX | Project 1 | 2024-02-01 | 50 | 1000
NX | Project 1 | 2024-02-01 | 50 | 1050
NX | Project 1 | 2024-02-01 | 50 | 1100
AD | Project 1 | 2024-02-01 | 50 | 1150
IS | Project 2 | 2024-02-01 | 50 | 1200
JT | Project 2 | 2024-02-01 | 50 | 1250
JT | Project 2 | 2024-02-01 | 50 | 1300
KU | Project 2 | 2024-02-01 | 50 | 1350
KU | Project 2 | 2024-02-01 | 50 | 1400
KU | Project 2 | 2024-02-01 | 50 | 1450
KU | Project 2 | 2024-02-01 | 50 | 1500
AD | Project 2 | 2024-02-01 | 50 | 1550
AD | Project 2 | 2024-02-01 | 50 | 1600
DL | Project 1 | 2024-03-01 | 50 | 1650
DL | Project 1 | 2024-03-01 | 50 | 1700
GQ | Project 1 | 2024-03-01 | 50 | 1750
LV | Project 1 | 2024-03-01 | 50 | 1800
NX | Project 1 | 2024-03-01 | 50 | 1850
IS | Project 2 | 2024-03-01 | 50 | 1900
JT | Project 2 | 2024-03-01 | 50 | 1950
KU | Project 2 | 2024-03-01 | 50 | 2000
HR | Project 3 | 2024-03-01 | 50 | 2050
MW | Project 3 | 2024-03-01 | 50 | 2100
KU | Project 2 | 2024-04-01 | 50 | 2150
LV | Project 2 | 2024-04-01 | 50 | 2200
OY | Project 2 | 2024-04-01 | 50 | 2250
AD | Project 2 | 2024-04-01 | 50 | 2300
PZ | Project 2 | 2024-04-01 | 50 | 2350
MW | Project 3 | 2024-04-01 | 50 | 2400
PZ | Project 3 | 2024-04-01 | 50 | 2450
PZ | Project 3 | 2024-04-01 | 50 | 2500
OY | Project 3 | 2024-05-01 | 50 | 2550
AD | Project 3 | 2024-05-01 | 50 | 2600
OY | Project 3 | 2024-06-01 | 50 | 2650

## Staff
Staff Initials | Project | Hours Required | Hours Completed | Hours Completed (%) | Hours Required (%) | Row Labels | Completed | Required
CH | Pilot | 180 | 171 | 95% | 5% | PZ | 96.39% | 3.611%
GQ | Pilot | 270 | 232 | 85.93% | 14.07% | AD | 92.41% | 7.593%
LV | Pilot | 270 | 221 | 81.85% | 18.15% | OY | 90.28% | 9.722%
MW | Pilot | 180 | 143 | 79.44% | 20.56% | NX | 81.67% | 18.33%
OY | Pilot | 360 | 338 | 93.89% | 6.111% | MW | 79.17% | 20.83%
AD | Pilot | 270 | 261 | 96.67% | 3.333% | LV | 89.17% | 10.83%
DL | Project 1 | 180 | 154 | 85.56% | 14.44% | KU | 81.11% | 18.89%
GQ | Project 1 | 270 | 242 | 89.63% | 10.37% | JT | 92.78% | 7.222%
HR | Project 1 | 360 | 341 | 94.72% | 5.278% | IS | 84.44% | 15.56%
IS | Project 1 | 180 | 130 | 72.22% | 27.78% | HR | 90.93% | 9.074%
LV | Project 1 | 270 | 267 | 98.89% | 1.111% | GQ | 91.67% | 8.333%
NX | Project 1 | 180 | 147 | 81.67% | 18.33% | DL | 85.56% | 14.44%
AD | Project 1 | 270 | 237 | 87.78% | 12.22% | CH | 95% | 5%
GQ | Project 2 | 270 | 263 | 97.41% | 2.593%
HR | Project 2 | 360 | 317 | 88.06% | 11.94%
IS | Project 2 | 180 | 174 | 96.67% | 3.333%
JT | Project 2 | 180 | 167 | 92.78% | 7.222%
KU | Project 2 | 180 | 146 | 81.11% | 18.89%
LV | Project 2 | 270 | 240 | 88.89% | 11.11%
OY | Project 2 | 360 | 320 | 88.89% | 11.11%
AD | Project 2 | 270 | 232 | 85.93% | 14.07%
PZ | Project 2 | 180 | 174 | 96.67% | 3.333%
GQ | Project 3 | 270 | 253 | 93.7% | 6.296%
HR | Project 3 | 360 | 324 | 90% | 10%
LV | Project 3 | 270 | 235 | 87.04% | 12.96%
MW | Project 3 | 180 | 142 | 78.89% | 21.11%
OY | Project 3 | 360 | 317 | 88.06% | 11.94%
AD | Project 3 | 270 | 268 | 99.26% | 0.7407%
PZ | Project 3 | 180 | 173 | 96.11% | 3.889%